## Slide 1
NOVA MVP — Software Launch Plan
End-to-End Project Management Strategy & Execution Framework Prepared by: Project Management Intern | Target Release: 10 Weeks

## Slide 2
1. Executive Summary & Business Objective
• Product: NOVA — AI-Powered Team Productivity Platform (B2B SaaS).
• Business Need: High-performing teams lack consolidated task tracking, velocity analytics, and automated AI priorities.
• Target Objective: Plan, execute, and launch NOVA MVP within a strict 10-week execution window (5 Agile Sprints).
• Team Allocation: 10 Cross-Functional Headcount (1 PM, 1 Prod Mgr, 1 UI/UX, 2 Flutter, 2 Frontend, 2 Backend, 1 QA, 1 DevOps).
• Key Milestone: 100% on-time release with zero P0 critical bugs and >90% feature delivery.

## Slide 3
2. Product Backlog & Prioritization (MoSCoW + RICE)
• Structured Backlog: 19 User Stories organized across 6 Core Epics (Auth, Project Mgmt, Task Engine, Team RBAC, Dashboard, AI Insights).
• RICE Scoring Formula: (Reach x Impact x Confidence) / Effort evaluated for data-driven prioritization.
• P0 Must-Haves (12 Stories): Core Auth, Project CRUD, Drag-and-Drop Task Kanban, Member Roles, Executive KPI cards.
• P1 Should-Haves (6 Stories): Forgot password, Task comments, Alerts engine, AI task recommendation MVP.
• P2 Could-Haves (1 Story): Advanced custom dashboard theme settings (deferred to V1.1).

## Slide 4
3. 10-Week Master Roadmap & Agile Sprints
• Sprint 1 (Weeks 1-2): Requirements, Auth APIs, DB Schemas, Figma UI Design Kit.
• Sprint 2 (Weeks 3-4): Workspace Engine, Project CRUD, Team Invites & Member RBAC.
• Sprint 3 (Weeks 5-6): Task Management Engine, Drag-and-Drop Kanban, Task Comments.
• Sprint 4 (Weeks 7-8): Executive KPI Dashboard, Alerts Worker, Rule-Based AI Engine.
• Sprint 5 (Weeks 9-10): QA Hardening, 10 UAT Scenarios, Security Audit, AWS Cloud Launch.

## Slide 5
4. Resource Planning & RACI Governance Matrix
• Accountable (A): Product Manager owns feature scope; PM Intern owns schedule, RACI & risks.
• Responsible (R): Engineering Lead (Architecture), Backend/Frontend Devs (Code), QA Lead (Testing), DevOps (Infra).
• Capacity Formula: 10 Headcount x 80 hrs/sprint x 80% Focal Factor = 640 Gross Hours (~40 Story Points/Sprint).
• Workload Balancing: Front-loaded UI/UX in Sprint 1; QA testing automated continuously across Sprints 2-5.

## Slide 6
5. Risk Management & Dependency Tracking
• Risk Management: 10 risks scored on Likelihood (1-5) x Impact (1-5); proactive mitigations assigned.
• Critical Risk R-01 (Backend API Delay): Mitigated by pairing backend devs & providing mock JSON stubs to frontend.
• High Risk R-03 (Sprint 5 QA Bottleneck): Mitigated by mandating developer unit tests & automated API regression.
• Dependency Tracker: 12 technical dependencies tracked across DB schemas, UI kits, AWS infrastructure, and store approvals.

## Slide 7
6. Case Study: Change Request CR-001 (Week 6 AI Feature)
• Request: Management requested 'AI Task Recommendations' in MVP during Week 6.
• Impact Analysis: Analyzed across Scope (+5 Pts), Timeline (+2 wks risk), Cost, Quality, and Resources.
• Trade-Off Evaluation: Evaluated 4 Options using a Weighted Decision Matrix (Schedule 30%, Quality 25%, Value 20%).
• Recommended Solution (Option D): Phased Rule-Based AI Engine Scope Swap (swapping out non-critical email digest to V1.1).
• Outcome: Delivered AI feature in MVP while keeping Week 10 release date 100% intact!

## Slide 8
7. Executive Project Health Dashboard (Week 4 Snapshot)
• Overall RAG Status: ON TRACK 🟢 (Schedule Performance Index SPI = 1.05, Cost CPI = 1.00).
• Progress Metrics: 42% overall completion (53 / 110 Story Points delivered; 86 tasks completed).
• Interactive Web Dashboard: Produced 'dashboard.html' featuring dynamic filters, KPI cards, and risk heatmaps.
• Live Product Mockup: Developed 'nova_app_demo.html' interactive dark-mode SaaS web prototype.

## Slide 9
8. User Acceptance Testing (UAT) & Sign-Off
• UAT Strategy: 5-Day testing window in Week 9 on AWS Staging environment with 6 external beta testers.
• Test Suite: 10 detailed step-by-step test scenarios covering Auth, Project CRUD, Kanban, Comments, KPIs, AI, and Mobile.
• Defect SLAs: P0 Blocker (<4 hrs), P1 Critical (<12 hrs), P2 Major (<24 hrs).
• Exit Benchmark: 100% scenario pass rate, 0 P0/P1 defects open, formal PM & QA sign-off.

## Slide 10
9. 5-Pillar Launch Checklist & War-Room Runbook
• Product: 100% P0 features ready, zero blocker bugs, scope freeze enforced.
• Technical: AWS ECS multi-AZ container cluster live, DB automated backups active, Sentry monitoring enabled.
• Marketing & Support: Landing page live, docs published, press release scheduled, SendGrid email drip active.
• War-Room Execution: T-0 hour-by-hour runbook (06:00 AM DB Migration -> 07:30 AM DNS Flip -> 08:15 AM Smoke Tests -> GO LIVE).

## Slide 11
10. Sprint Retrospective & Continuous Improvement
• What Went Well: Cross-functional collaboration, MoSCoW prioritization, proactive scope management, fast API mock deployment.
• What Needed Improvement: Initial DB schema complexity, QA bottleneck risk during mid-sprint code drops.
• Action Items: Establish Swagger API contract freeze by Day 3 of each sprint; increase automated test coverage to 85%.

## Slide 12
11. Summary & Candidate Portfolio Conclusion
• Proven PM Competencies: Requirements breakdown, Agile sprint planning, EVM metrics, risk management, stakeholder comms.
• Complete Deliverable Package: Excel Workbook, Interactive Web Dashboard, Product Mockup, 12-Slide Deck, 9 Reports.
• Final Outcome: NOVA MVP launched on time, within budget, with high quality and recruiter-grade execution excellence!