## Overview & Governance
NOVA MVP — Master Project Overview
AI-Powered Team Productivity Platform (10-Week Agile Launch Plan)
Project Parameter | Details
Product Name | NOVA (SaaS Team Productivity Platform)
Project Duration | 10 Weeks (5 Agile Sprints x 2 Weeks)
Target Launch Date | Week 10 (Friday Release)
Total Team Size | 10 Headcount (1 PM, 1 Prod Mgr, 1 UI/UX, 2 Flutter, 2 Front-End, 2 Backend, 1 QA, 1 DevOps)
Primary PM Methodology | Agile Scrum + MoSCoW & RICE Prioritization
Overall Project Status | ON TRACK (Week 4 Snapshot: 42% Complete, SPI = 1.05, CPI = 1.00)
Key Business Goal | Launch robust MVP to enable team task mgmt, collaboration, dashboard, and AI insights.

## Product Backlog
Story ID | Epic | Feature | User Story Description | Acceptance Criteria | MoSCoW | Reach | Impact | Confidence | Effort | RICE Score | Story Points | Sprint | Owner
US-01 | Authentication | Sign Up | As a user, I want to create an account so I can access NOVA. | Validates email, password strength, sends verification link. | P0 (Must) | 1000 | 3 | 0.9 | 2 |  | 3 | Sprint 1 | Backend Dev 1
US-02 | Authentication | Login | As a user, I want to log in securely so I can access my workspace. | JWT token issued, error message on invalid credentials. | P0 (Must) | 1000 | 3 | 0.9 | 2 |  | 3 | Backend Dev 1
US-03 | Authentication | Forgot Password | As a user, I want to reset my password if forgotten. | Generates secure reset token via email. | P1 (Should) | 500 | 2 | 0.8 | 2 |  | 3 | Backend Dev 2
US-04 | Authentication | User Profile | As a user, I want to update my avatar and profile details. | Allows updating name, title, profile picture. | P1 (Should) | 800 | 2 | 0.9 | 1 |  | 2 | Front-End Dev 1
US-05 | Project Management | Create Project | As a team lead, I want to create a new project workspace. | Project title, key, description, start/end dates. | P0 (Must) | 1000 | 3 | 0.9 | 3 |  | 5 | Backend Dev 2
US-06 | Project Management | Edit Project | As a project owner, I want to modify project details. | Updates project settings, owner permissions enforced. | P0 (Must) | 800 | 2 | 0.9 | 2 |  | 3 | Front-End Dev 2
US-07 | Project Management | Delete Project | As an admin, I want to archive or delete a project. | Soft delete with confirmation modal. | P1 (Should) | 500 | 2 | 0.8 | 1 |  | 2 | Backend Dev 1
US-08 | Project Management | Project Dashboard | As a manager, I want a high-level project view. | Shows project status, task counts, timeline progress. | P0 (Must) | 1000 | 3 | 0.9 | 3 |  | 5 | Flutter Dev 1
US-09 | Task Management | Create Task | As a team member, I want to create tasks within a project. | Inputs title, description, priority, assignee, due date. | P0 (Must) | 1000 | 3 | 0.9 | 3 |  | 5 | Backend Dev 1
US-10 | Task Management | Assign Task | As a lead, I want to assign tasks to team members. | Assignee receives task, update logged in activity history. | P0 (Must) | 1000 | 3 | 0.9 | 2 |  | 3 | Front-End Dev 1
US-11 | Task Management | Task Priority & Due Date | As a user, I want to set task priority (Low, Med, High, Urgent). | Visual priority badges and due date picker. | P0 (Must) | 1000 | 2 | 0.9 | 1 |  | 2 | Flutter Dev 2
US-12 | Task Management | Task Status Workflow | As a user, I want to move tasks (To Do, In Progress, Review, Done). | Kanban drag-and-drop or status dropdown. | P0 (Must) | 1000 | 3 | 0.9 | 3 |  | 5 | Front-End Dev 2
US-13 | Task Management | Task Comments | As a member, I want to comment on tasks to collaborate. | Rich text comments with timestamps. | P1 (Should) | 800 | 2 | 0.8 | 2 |  | 3 | Backend Dev 2
US-14 | Team Management | Add/Remove Members | As an admin, I want to manage project members. | Invite via email, role assignment (Admin, Member, Viewer). | P0 (Must) | 900 | 3 | 0.9 | 2 |  | 3 | Backend Dev 1
US-15 | Team Management | Member Roles | As an admin, I want role-based access control (RBAC). | Enforces view/edit/delete permissions across objects. | P0 (Must) | 900 | 3 | 0.9 | 3 |  | 5 | Backend Dev 2
US-16 | Dashboard | Executive KPIs | As an executive, I want to view active/completed/overdue tasks. | Displays numerical KPI cards and completion progress bars. | P0 (Must) | 1000 | 3 | 0.9 | 3 |  | 5 | Front-End Dev 1
US-17 | Dashboard | Team Productivity | As a manager, I want to track team velocity and workload. | Generates completion breakdown by team member. | P1 (Should) | 700 | 2 | 0.8 | 3 |  | 5 | Front-End Dev 2
US-18 | Notifications | In-App & Email Alerts | As a user, I want notifications when assigned tasks or due dates change. | Triggers real-time alerts and daily digest email. | P1 (Should) | 800 | 2 | 0.8 | 2 |  | 3 | Backend Dev 1
US-19 | AI Insights | AI Task Recommendations | As a user, I want smart task priority suggestions based on deadlines. | Heuristic recommendation engine suggests next priority task. | P1 (Should) | 600 | 3 | 0.7 | 3 |  | 5 | Backend Dev 2

## Sprint Schedule
Sprint | Weeks | Sprint Goal | Key Deliverables | Target Points | Velocity Target | Status
Sprint 1 | Weeks 1-2 | Foundation, Auth & Architecture Setup | Auth APIs, User DB Schema, Flutter/Web scaffolding, CI/CD | 25 | 25 pts | COMPLETED
Sprint 2 | Weeks 3-4 | Core Project Management & RBAC Engine | Project CRUD, Workspace Dashboard, Member Invites & Roles | 28 | 28 pts | COMPLETED
Sprint 3 | Weeks 5-6 | Core Task Management & Collaboration Engine | Task CRUD, Priority/Due dates, Kanban Workflow, Task Comments | 30 | 30 pts | IN PROGRESS
Sprint 4 | Weeks 7-8 | Executive Dashboard, Notifications & AI MVP | Metrics Dashboard, Team Productivity, In-App Alerts, AI Rules Engine | 26 | 26 pts | PLANNED
Sprint 5 | Weeks 9-10 | QA Hardening, UAT Execution & Production Launch | Full E2E Testing, Bug Fixes, Security Audit, Cloud Deployment | 20 | 20 pts | PLANNED

## RACI Resource Matrix
Workstream / Phase | Product Mgr | Project Mgr | UI/UX Designer | Flutter Devs | Frontend Devs | Backend Devs | QA Engineer | DevOps Eng
Requirements & Scope Definition | Accountable (A) | Responsible (R) | Consulted (C) | Informed (I) | Informed (I) | Consulted (C) | Informed (I) | Informed (I)
UI/UX Design & Wireframing | Consulted (C) | Accountable (A) | Responsible (R) | Consulted (C) | Consulted (C) | Informed (I) | Informed (I) | Informed (I)
Database & API Development | Informed (I) | Accountable (A) | Informed (I) | Consulted (C) | Consulted (C) | Responsible (R) | Consulted (C) | Consulted (C)
Mobile & Web Frontend Dev | Informed (I) | Accountable (A) | Consulted (C) | Responsible (R) | Responsible (R) | Consulted (C) | Informed (I) | Informed (I)
Quality Assurance & Bug Tracking | Informed (I) | Accountable (A) | Informed (I) | Consulted (C) | Consulted (C) | Consulted (C) | Responsible (R) | Informed (I)
DevOps & Production Deployment | Informed (I) | Accountable (A) | Informed (I) | Informed (I) | Informed (I) | Consulted (C) | Consulted (C) | Responsible (R)
UAT Execution & Client Sign-off | Accountable (A) | Responsible (R) | Consulted (C) | Support (S) | Support (S) | Support (S) | Responsible (R) | Informed (I)

## Risk Register
Risk ID | Category | Risk Description | Likelihood (1-5) | Impact (1-5) | Severity (L x I) | Severity Level | Mitigation Strategy | Owner
R-01 | Technical | Backend API delivery delayed due to complex DB schema. | 4 | 4 |  | CRITICAL (16) | Start API contract design in Sprint 1; pair backend devs. | Backend Lead
R-02 | Scope | Scope creep: Unplanned AI feature requested in Week 6. | 4 | 3 |  | HIGH (12) | Establish Change Control Board (CCB); use Phase 1 heuristic scope swap. | Project Manager
R-03 | Resource | QA bottleneck during Sprint 5 testing window. | 3 | 4 |  | HIGH (12) | Implement developer unit testing and automated integration tests in Sprints 2-4. | QA Lead
R-04 | Design | UI/UX wireframe delays block front-end implementation. | 3 | 3 |  | MEDIUM (9) | Front-load design reviews; complete component library by end of Sprint 1. | UI/UX Designer
R-05 | DevOps | Production environment configuration failure on launch day. | 2 | 4 |  | MEDIUM (8) | Deploy staging environment in Sprint 2; run full dry-run deployment in Sprint 4. | DevOps Engineer
R-06 | Security | Authentication vulnerability or unencrypted token leak. | 2 | 5 |  | HIGH (10) | Implement JWT standard with HTTPS, bcrypt password hashing, and security audit. | Backend Dev 1
R-07 | Integration | Flutter mobile app and Web frontend UI state mismatch. | 3 | 3 |  | MEDIUM (9) | Share unified OpenAPI/Swagger specification across mobile and web teams. | Engineering Lead
R-08 | Dependency | Third-party email notification service downtime. | 2 | 3 |  | MEDIUM (6) | Abstract notification handler with fallback queuing (Redis/Celery). | Backend Dev 2
R-09 | Performance | Dashboard slow response time under heavy task load. | 2 | 4 |  | MEDIUM (8) | Add DB indexing on task status and project IDs; implement caching. | Backend Lead
R-10 | Stakeholder | Delayed UAT sign-off from executive management. | 3 | 3 |  | MEDIUM (9) | Conduct weekly demo showcases; align UAT criteria at start of Sprint 4. | Product Manager